## Dashboard
Audspect / BAS — Findings Dashboard
Auto-updates from the Findings Tracker. Severity x Likelihood drives Risk Score.
21 |  | 5 |  | 3 | 8 |  | 5
TOTAL FINDINGS |  | CRITICAL |  | HIGH | MEDIUM |  | LOW
20 |  | 0 |  | 0 | 0% |  | 7
OPEN |  | IN PROGRESS |  | RESOLVED | % RESOLVED |  | OPEN CRIT+HIGH
By Severity |  |  | By Status |  | By Priority Wave
Severity | Count |  | Status | Count | Wave | Count
Critical | 5 |  | Open | 20 | Wave 0 | 1
High | 3 |  | In Progress | 0 | Wave 1 | 6
Medium | 8 |  | Fixed | 0 | Wave 2 | 4
Low | 5 |  | Verified | 0 | Wave 3 | 5
|  |  | Won't Fix | 0 | Wave 4 | 5
|  |  | Deferred | 0

## Findings Tracker
Audspect / BAS — Security & Maturity Findings Tracker
Live tracker — edit the Severity, Likelihood, Effort, Wave, Status, Owner, Target Date and Notes columns; Risk Score/Rating and the Dashboard update automatically.
ID | Area | Finding | Location (file:line) | Severity | Likelihood | Risk Score | Risk Rating | Business Impact | Root Cause | Suggested Fix | Better / Alternative Approach | Impact of Fixing | Effort | Priority Wave | Status | Owner | Target Date | Notes
A1 | Secrets | Live credentials committed to the repo (AWS / OpenRouter / OIDC) | keys.txt, tenantID.txt, setting.json, Model Configurator.txt (repo root) | Critical | High | 12 | Severe | Anyone with the repo or its git history has working cloud/LLM/identity credentials -> possible AWS account takeover, LLM billing abuse, IdP abuse. Most urgent item. | No secret-management boundary: secrets live in files inside the repo and nothing blocks committing them. | 1) Rotate/revoke ALL exposed creds now (assume compromised). 2) Purge from git history (git filter-repo / BFG) + force-push. 3) Add to .gitignore + move to env vars / secrets manager (code already reads them from env). | Add gitleaks/trufflehog as a pre-commit hook AND a CI gate that fails the build on any detected secret, so this can never recur. | Removes an active breach path; nothing changes at runtime (app reads secrets from env/config). Restores trust for a security-vendor audience. | Low | Wave 0 | Closed |  |  | Manually deleted
B1 | Agent Trust | Shared fleet-wide agent secret + guessable AgentID | agent/identity.go, agent/config.go | Critical | Medium | 8 | High | One leaked endpoint secret can impersonate any agent; no per-agent authentication boundary. AgentID = SHA-256(hostname)[:16] is guessable. | Auth modeled as a single shared bearer secret instead of per-agent identity. | Issue per-agent credentials at enrollment (mTLS client cert OR per-agent token bound to agent_id, stored hashed). Keep a short-lived, rotated enrollment secret only to bootstrap the first credential. | Prefer mTLS client certs (orchestrator as private CA) - also solves transport auth (B3) in one move. | Shrinks blast radius from 'whole fleet' to 'one host'; extends the existing enrollment flow, so live deployments migrate on next enroll. | Medium | Wave 2 | Open
B2 | Agent Trust | Agent secret transmitted in the WebSocket URL query string | agent/protocol/websocket.go:47; server: internal/api/handlers.go:238-242 | Critical | High | 12 | Severe | Secret leaks into proxy logs, load-balancer logs, and server access logs across the network path. | Convenience - query params are the easiest thing to set on a WS dial. | Send the credential in a handshake HEADER (gorilla Dial supports http.Header) or WS subprotocol, never the URL. Remove the ?agentSecret= fallback on the server once agents are updated. | Server already prefers the X-Agent-Token header - just make header the ONLY accepted path. | Stops credential disclosure via logs; no user-visible behavior change. Roll agents first, then delete the fallback. | Low | Wave 1 | Open
B3 | Agent Trust | No TLS certificate pinning; plaintext ws:// default | agent/config.go (default http://localhost:9000); agent/agent.go (~1210) | Critical | Medium | 8 | High | A MITM presenting any trusted cert - or intercepting plaintext ws:// in a misconfig - gets fleet-wide SYSTEM/root RCE. | Transport security left to defaults; no pinning; plaintext allowed unconditionally. | Pin the orchestrator cert/public key (ship expected SPKI hash at enrollment; verify in tls.Config.VerifyPeerCertificate). Refuse plaintext ws:// unless an explicit --dev flag is set. | With mTLS (B1) this becomes mutual pinning - strongest option for on-prem where you control both ends. | Eliminates MITM path to RCE; on-prem operators control both ends so pinning is invisible to users. | Medium | Wave 1 | Open
B4 | Agent Trust | Server commands not signed; no local allow-list | agent/agent.go:1249-1341; agent/executor*.go | Critical | Medium | 8 | High | After the handshake any well-formed WS frame is executed verbatim; a rogue/compromised orchestrator = arbitrary code on every endpoint. | Trust placed entirely in the channel + server-side curation, with nothing verifiable at the agent. | Sign scenario/command bundles server-side with the EXISTING RSA signing infra; agent verifies against a pinned public key baked at install before executing. | Combine with B5 (local destructive-action guardrail) for defense-in-depth; even a compromised orchestrator process can't forge commands without the offline signing key. | Reduces impact of orchestrator compromise from 'total' to 'cannot run unsigned commands'. Scenarios are already signed, so legit content is unaffected. | Medium | Wave 2 | Open
B5 | Agent Safety | No destructive-action guardrail on the agent | agent/sched/riskgate.go; agent/snapshot_*.go | High | Medium | 6 | High | Reversibility covers only enumerated persistence surfaces; a destructive command outside them (real encryption, rm -rf, format) runs irreversibly as SYSTEM/root. | 'Safety' delegated 100% to server-side curation; the agent has no independent notion of 'destructive'. | Add a local, signed allow-list/denylist the agent enforces pre-execution (allowed executors, blocked wiper/format/mass-write patterns, file-mod rate cap). Fail-closed. | Map the guardrail to the existing Posture/Telemetry/Lab tiers so Telemetry stays production-safe and only signed Lab grants unlock full tradecraft. | Makes irreversible endpoint damage structurally impossible; preserves the intended 3-tier fidelity model, now enforced at the endpoint too. | Medium | Wave 2 | Open
C1 | Multi-tenancy | Row-Level Security designed but disabled (isolation not enforced) | internal/db/postgres.go:1256-1271; internal/db/tenant.go | High | Medium | 6 | High | Any query path that forgets the tenant filter leaks cross-tenant data. Claiming multi-tenant isolation today would be inaccurate. | Multi-tenancy shipped as scaffolding (columns + seam) pending a 'future migration'; ENABLE/FORCE RLS left commented; WithTenant used in ~5 places. | ENABLE+FORCE RLS on every tenant table (policy USING tenant_id = current_setting('app.tenant_id')). Route ALL request DB access through WithTenant. Turn on the existing DB role hardening (NOBYPASSRLS). Add cross-tenant isolation tests. | For single-tenant on-prem, set one default tenant so RLS is a no-op that still hardens the path - enable it now with zero behavior change; it becomes load-bearing only if you sell SaaS. | Turns claimed isolation into enforced isolation; unblocks any future multi-tenant SaaS offering. DECISION NEEDED: finish this, or scope messaging to single-tenant on-prem. | Large | Wave 3 | Open
D1 | Supply Chain | No Authenticode / macOS notarization on binaries | packaging/signing/* (GPG-only) | High | Medium | 6 | High | Windows agent+installer and macOS binaries are unsigned for OS trust -> SmartScreen/Gatekeeper friction, easier trojanization, weaker enterprise trust for a security vendor. | Signing pipeline built for air-gapped GPG verification, never extended to OS-native code signing. | Add Authenticode (signtool /fd sha256 /tr <timestamp>) for Windows agent+installer; codesign + notarize + staple for macOS, using an HSM/EV cert in the release pipeline. | Keep GPG for air-gapped verification (belt and suspenders). | Removes install-time warnings, raises supply-chain assurance for BFSI buyers; purely additive - runtime behavior unchanged. | Medium | Wave 2 | Open
D2 | Supply Chain | Agent binary not obfuscated (documented) | packaging/build.sh:48 | Low | Low | 1 | Low | Agent strings/symbols are trivially reversible, easing evasion. Lower severity than the trust items. | Toolchain incompatibility (garble vs x/sys assembly); only the orchestrator is garbled. | Selectively obfuscate packages that don't pull x/sys asm, or adopt a garble config that tolerates it. | Accept that endpoint agents are inherently reversible and rely on B1-B4 (identity + signing) for security; treat obfuscation as defense-in-depth only, not a control. | Marginally raises reverse-engineering cost; not a security control on its own. | Medium | Wave 4 | Open
F1 | API / Web | Non-constant-time agent-secret comparison | internal/api/handlers.go:242 | Medium | Low | 2 | Low | String == on a secret is a timing side-channel; theoretical secret recovery. | Default comparison used for a secret value. | Use subtle.ConstantTimeCompare([]byte(provided),[]byte(secret)) == 1. | Becomes moot once B1 per-agent tokens land, but fix regardless (one line). | Closes a timing side-channel; trivial change, no behavior impact. | Low | Wave 1 | Open
F2 | API / Web | CORS wildcard on the Python API | api/main.py:38-40 | Medium | Medium | 4 | Elevated | allow_origins=['*'] with '*' methods/headers lets any origin call the API from a browser (CSRF / data exposure). | Permissive default left in. | Set allow_origins to the explicit console origin(s) from config; drop wildcard methods/headers to the actual set used; never combine '*' origins with credentials. | The SPA is same-origin (served by the orchestrator), so locking origins doesn't break it. | Removes cross-origin data-exposure surface; no impact on the real console. | Low | Wave 1 | Open
F3 | API / Web | Browser WebSocket CheckOrigin always returns true | internal/ws/hub.go:17 | Medium | Medium | 4 | Elevated | The browser hub upgrader accepts any origin -> cross-site WebSocket hijacking of the browser channel. | Placeholder permissive check. | Validate Origin against the configured public base URL / allowed origins for browser connections; keep the credentialed agent WS path separate. | Legit console connects same-origin, so validation is invisible to users. | Closes a CSWSH vector; no user-visible change. | Low | Wave 1 | Open
F4 | API / Web | No JWT secret entropy/length check | orchestrator/config/config.go:280-281 | Medium | Medium | 4 | Elevated | A weak/short JWT_SECRET is accepted; HS256 security depends entirely on secret entropy -> forgeable tokens. | Presence of the secret is checked, strength is not. | Require >=32 bytes (reject known-default/low-entropy values); fail closed at boot with a clear message. Optionally support RS256 with a keypair for large deployments. | Existing strong secrets pass; only weak ones are rejected - which is the point. | Prevents token forgery from weak secrets; fails safely at startup. | Low | Wave 1 | Open
G1 | Frontend | XSS surface: 455 innerHTML sinks + duplicated inconsistent escaper | orchestrator/wwwroot/index.html | Medium | Medium | 4 | Elevated | Server/imported data flows into innerHTML with inconsistent escaping (escaper redefined >=4x with differing behavior) -> plausible stored XSS -> console/session compromise. | No single canonical escaper; DOM built by string concatenation; no sanitizer; monolithic file makes consistency hard. | Define ONE canonical escapeHTML(), remove duplicates, rename the shadowing numeric 'x'. Audit all 455 sites: prefer textContent; escape all interpolated HTML or use DOMPurify. Add a lint/CI grep for new raw innerHTML. | Add a Content-Security-Policy header (nonces/hashes) as defense-in-depth, planned alongside G2 modularization. | Neutralizes stored-XSS paths; rendering of benign data is identical. | Medium | Wave 3 | Open
G2 | Frontend | Monolithic 22k-line single-file SPA, no build/tests | orchestrator/wwwroot/index.html | Low | Medium | 2 | Low | Unmaintainable, untestable UI; amplifies G1 recurrence risk. | Grew organically without a module/build system. | Introduce a build step; split into modules; add UI tests; enables a strict CSP. | Do this incrementally behind the existing boot-time integrity hash so releases stay verifiable. | Long-term maintainability + testability; removes the structural cause behind repeated XSS risk. | Large | Wave 4 | Open
H1 | Data Layer | No versioned DB migrations (boot-time idempotent DDL) | internal/db/postgres.go (~110KB of CREATE/ALTER IF NOT EXISTS) | Medium | Medium | 4 | Elevated | Schema evolution is implicit/unversioned: risky column drops, no rollback, no audit, environment drift. | Migrations deferred in favor of idempotent bootstrap; no schema-version table. | Adopt golang-migrate/goose with a schema_migrations table; snapshot current schema as baseline; ship every change as numbered up/down; run as an explicit --migrate deploy step. | Baseline migration reproduces today's schema exactly, so behavior is unchanged while upgrades become auditable and reversible. | Makes upgrades/rollbacks safe and auditable; prevents drift across customer installs. | Medium | Wave 3 | Open
I1 | Observability | Observability exporters are no-op stubs | internal/observability/exporters.go:15-29; otel.go/alerting.go TODOs | Medium | Medium | 4 | Elevated | No external metrics/traces/alert delivery -> running in production partially blind (operational, not a direct vuln). | Feature scaffolded; exporters never implemented (8 of 9 non-test TODOs live here). | Implement Prometheus remote-write / OTLP exporters and webhook alert delivery; wire alerting to the (already real) metrics registry. | Gate /metrics with the existing MetricsToken (already supported). | Gives production visibility + alerting; closes an operational blind spot. | Medium | Wave 3 | Open
I2 | Testing | internal/siem package untested | orchestrator/internal/siem (446 LOC, 0 tests) | Low | Medium | 2 | Low | Only sizeable untested package; SIEM-correlation regressions go undetected. | Test coverage gap. | Add unit + integration tests (testcontainers harness already exists). | Add a CI coverage gate so no package ships large + untested again. | Prevents silent regressions in a core correlation path. | Low | Wave 3 | Open
J1 | Hygiene | 53MB unused vendored OpenAEV + licensing exposure | openaev-main/ (4,759 files) | Medium | Medium | 4 | Elevated | Repo bloat + licensing risk: EE-headered files vendored into a commercial repo; even Apache-2.0 CE requires retaining NOTICE/attribution. Not built or served. | A reference checkout was dumped into the tree instead of referenced as a dependency. | Delete openaev-main/; document the external OpenAEV version the connector targets. If any is truly needed, pin it as a proper dependency with LICENSE/NOTICE preserved. | Audspect integrates via the clean internal/openaev connector to an external instance - the source dump is not needed. | Removes a legal exposure and ~53MB of bloat; no functional impact. | Low | Wave 4 | Open
J2 | Hygiene | Unrelated .agents marketing toolkit committed | .agents/ (157 files) | Low | Low | 1 | Low | Confusing, unrelated content (Mehendi/nail-product placeholders) in a security product repo. | Accidental commit of an unrelated toolkit. | Remove the directory. | Verify nothing in the build references it first (it doesn't). | Cleaner repo; removes confusion for new engineers/auditors. | Low | Wave 4 | Open
J3 | Hygiene | ~40MB media/binaries at repo root | *.mp4, *.PNG, sample PDFs, 10MB CSV, *.docx, BASAgent.pdb | Low | Low | 1 | Low | Slow clones, bloated history. | Binaries committed directly to git. | Move to Git LFS or an artifact store; keep the repo to source + small assets. | Consider a history rewrite (with the A1 purge) to reclaim history size. | Faster clones/CI; leaner history. | Low | Wave 4 | Open

## Legend & How-to-use
Legend & How to use this tracker
How to use
• Work only in the Findings Tracker tab. Edit the coloured dropdown columns and the free-text Owner/Target/Notes.
• Risk Score = Severity weight (Critical4/High3/Medium2/Low1) x Likelihood weight (High3/Med2/Low1). It recalculates when you change the dropdowns.
• The Dashboard tab auto-updates from the tracker via COUNTIF formulas — no manual edits needed there.
• To add a finding, type in the first empty row inside the table; the table and dropdowns extend automatically. The Risk Score/Rating formulas auto-fill.
• Rows marked Fixed or Verified are tinted green in the ID column.
Severity
Critical | Exploitable now / active exposure; fix immediately (breach path or fleet-wide RCE).
High | Serious weakness; enforce before production / GA.
Medium | Real risk; schedule within the normal hardening cycle.
Low | Hygiene / minor; fix opportunistically.
Status values
Open | Not started.
In Progress | Being worked on.
Fixed | Change made, awaiting verification.
Verified | Fix confirmed effective.
Won't Fix | Accepted risk / out of scope (document why in Notes).
Deferred | Planned for a later wave.
Priority Waves (from the assessment report)
Wave 0 | Today — contain the breach (rotate & purge committed secrets).
Wave 1 | Sprint 1 — shrink the RCE blast radius (transport, CORS, WS origin, JWT, header auth).
Wave 2 | Sprint 2-3 — finish the agent trust model (per-agent creds, command signing, guardrail, code signing).
Wave 3 | Sprint 4+ — production maturity (RLS, migrations, observability, XSS, tests).
Wave 4 | Cleanup & strategy (repo hygiene, obfuscation, modularize SPA).
Source
Report | AUDSPECT_ASSESSMENT_REPORT.md (repo root) — full narrative, root causes and code-level fixes.
Generated | 2026-09-26, from a full static review + live local deployment. Secret values intentionally omitted.